## SKA_MGR_WBS_Document
Request for Expression of Interest (EoI) for Pre-construction Phase of the Square Kilometre Array
SKA MGR WBS Document Detailed explanation of the Work Breakdown Structure of Telescope Manager Element
3. SKA TEL MGR Telescope Manager
4. SKA.TEL.MGR.MGT telescope manager engineering management |  |  | This WBS element covers all the activities that will be required to support the development of a comprehensive Project Management Plan (PMP) for the SKA (Stage 1) and a first draft for Stage 2 .
| 5 SKA.TEL.MGR.MGT.APP - Project Management Plan |  | This WBS element covers all the activities that will be required to plan, conduct and manage project meetings at and within the element of the project. Report templates for the various official meetings will be developed and utilised but in general reporting will be done against the majority of the project management WBS elements.
| 5 SKA.TEL.MGR.MGT.MTG - Meetings |  | This WBS element covers all the activities that will be required to conduct and manage the costing effort within the element. The costing within this WBS element does not refer to the management and reporting of the actual costs incurred by members of the WPC, it refers to the full life cycle costing of the SKA1 and SKA2 systems. Deliverables: Costing reports in stage 1 Requirements Definition, stage 1 Preliminary Design and stage 2 Detailed Design and Qualification, including development, construction, verification, commissioning and steady state operations costs.
| 5 SKA.TEL.MGR.MGT.CST - Costing |  | This WBS element covers all the activities that will be required to define and implement tools and systems to effectively conduct and manage communication, horizontal and vertical, within the project. Because of its distributed nature and collaborative efforts, clear and uninhibited communication will be critical to the success of the project. It will be the responsibility of the project manager(s) to ensure that mechanisms and monitoring activities are in place to continuously monitor and manage these aspects. Apart from written communication it is foreseen that regular telecons, videocons and visits will take place.
| 5 SKA.TEL.MGR.MGT.COMM - Communication Plan |  | This WBS element includes all the management effort in the establishing, resourcing and management of the activities of Integrated Task Teams (ITTs) at Element level. The technical work for the interfaces to be produced by the interface development teams are covered in the items: 4. SKA.TEL.MGR.SE telescope manager system engineering 5. SKA.TEL.MGR.SE-PDR.EIRD - Telescope Manager Define External Interface Requirements 5. SKA.TEL.MGR.SE-PDR.EICD - Telescope Manager Define External Interfaces.
| 5 SKA.TEL.MGR.MGT.ITT - Integrated Task Teams |  | This WBS element covers activities to: - plan risk management, - manage the risk profile, - analyse, treat and monitor risks, - evaluate risk management process - report risks and mitigation strategies by maintaining a risk register. Deliverables: - TM Risk Register
| 5. SKA.TEL.MGR.MGT.RMT - Telescope Manager Risk Management |  | This WBS element covers the governance plan of the SKA TM consortium. This will include the consortium organisation chart, responsibilities of the roles indicated in the organisation chart
| 5 SKA.TEL.MGR.MGT.GOV - Governance model |  | This WBS element covers the plan for formation of the review committee for monitoring the project health/ progress.
| 5 SKA.TEL.MGR.MGT.REV - Review Comittee |  | This WBS element covers all the activities involved in monitoring the project health. This will include: - Who will keep the over track of the project - The progress reporting mechanism (Within consortium as well as to the SPO) - Frequency/ duration of the reviews - Types of reviews and their scope
| 5 SKA.TEL.MGR.MGT.MON - Project Monitoring |  | This WBS element covers all the activities that will be required to plan and formulate a strategy to handle the changes in scope of work from time to time. The change management plan will include the brief change management procedure describing Who can initiate the change request, Who can approve the change request etc.
| 5 SKA.TEL.MGR.MGT.CHG - Change Management |  | This WBS element covers all the activities that will be needed to perform during a crisis by the respective process owners. The objective of having a crisis management plan is to have a plan in place for project continuity during and after a disaster. This will include: Mitigation planning Continuity planning Disaster recovery planning
| 5 SKA.TEL.MGR.MGT.CRIS- Crisis Management |  | This WBS element covers all the activities involved in subcontracting the work to the vendor, such as identification of the vendor, finalizing the vendors, defining the criteria for finalizing the vendor, vendor quality management, communication with the vendor etc.
| 5 SKA.TEL.MGR.MGT.VEN- Vendor Management |  | This WBS element covers all the activities required to keep the project team updated with the necessary tools and technologies for working effectively on the project. Plan for Identification of the training needs, trainers, training mode and methodologies (web based trainings/ instructor), induction plan for new team members etc. will be provided here.
| 5 SKA.TEL.MGR.MGT.TRAIN- Training and Competency Plan |  | This WBS element covers all the activities required to plan the documentation needs of the TM manager, including the tools/ versions to be used, documentation guidelines, document naming conventions, standard templates etc.
| 5 SKA.TEL.MGR.MGT.DOC - Documentation Plan |  | This WBS element covers all the activities related to planning of the obsolescence of the hardware and software components of the telescope manager. Identification of the End of Life plan of the HW and SW components, stocking of the spares, up gradation of the existing sw and hw components, establishing annual maintenance contracts with vendors, extending the warranty support etc.
| 5 SKA.TEL.MGR.MGT.OBS - Obsolescence Management |  | PM tools, requirement management tools (e.g. Vitec CORE), software modeling tools (e.g. Rhapsody for UML). [TCS to describe]
| 5 SKA.TEL.MGR.MGT.TOOLS - Enterprise Management and Common Tools |  | This WBS element covers the system engineering activities for the TM element on level 3. The requirements, design and interfaces work are directed to level 3 TM and thus are only between level 4 TM subsystems and not lower (i.e. Telescope Management, Observation Management, Prototypes, Local M&C and TM Infrastructure). The next level requirements engineering, architectural design and interface identificaiton and definition for each of the level 4 TM subsystems will in turn be done as level 5 items under each of these level 4 TM subsystems.
4. SKA.TEL.MGR.SE telescope manager system engineering |  |  | This WBS element covers the activities to define systems engineering management for the TM consortium for stages 1 and 2, using the SKA RfP documents and the TM SEMP Summary as inputs. Deliverable: - TM SEMP
| 5. SKA.TEL.MGR.SE.APP - Telescope Manager Systems Engineering Approach |  | This WBS element covers activities to: - Maintain information on configurations with an appropriate level of integrity and security - Ensure that changes to configuration baselines are properly identified, recorded, evaluated, approved, incorporated and verified. - Do software version control, configuration status and release management ( refer to IEEE Std 12207-2008 par. 7.2.2) Refer to the Work Identification Matrix “Perform configuration management” process. Deliverables: - ECPs, baselines
| 5. SKA.TEL.MGR.SE.CC - Telescope Manager Perform Configuration Control |  | This WBS element covers activities to: - Verify that the System Engineering process, as described in the SEMP, is being followed consistently and thoroughly. - Ensure that the software being developed meets the minimum quality standards for this specific application
| 5.SKA.TEL.MGR.SE.PASS - Telescope Manager Product Assurance |  | This WBS element covers implementation and management of common software environment for the TM. (Can include things like build framework, test environment, code repositories, coding standards, operating systems, databases, etc) Excludes modelling tools - these are covered under 5 SKA.TEL.MGR.MGT.TOOLS.
5. SKA.TEL.MGR.SE.SDE - Software Development Environment
| 5. SKA.TEL.MGR.SE.RE - Telescope Manager Requirements Engineering |  | This WBS element covers requirements engineering activities during stage 1 Requirements Definition to support concept definition of the TM on level 3. Architecture driving, cost driving and risky requirements are analysed and clarified, with the SKA1 baseline design as input. Inputs: - SKA1 System Baseline Design [5] - SKA1 DRM and other SKA RFP documentation - M&C CoDR, ASKAP, ALMA and MeerKAT Requirement Specs Tasks : Time boxed requirements analysis to identify the critical requirements: - Define architecture driving requirements - Define cost driving requirements - Define requirements that may pose technical risks Refer to processes “Define System Requirements” and “Analyse and Maintain System Requirements” in the TM work identification matrix for more detail. Deliverable: - Draft TM Requirements Specification (Level 3)
|  | 6. SKA.TEL.MGR.SE.RE.CONCEPT - Telescope Manager Requirements Engineering - concept definition | This WBS element covers Requirements Engineering activities to provide a full set of requirements, excluding external interface requirements for PDR. These requirements shall include functional, performance, reliability, maintainability, environmental, safety and design constraints. Tasks (refer to TM Work Identification Matrix “Requirements Engineering” process for more detail): - Analyse all requirements - Interaction with SKA SE and other elements Inputs: - SKA1 System Baseline Design [5] - SKA Telescope Requirements Specification ??? - SKA Concept of Operation ??? Deliverable: - Updated TM Requirement Specification (Level 3)
|  | 6. SKA.TEL.MGR.SE.RE.RR- Telescope Manager Requirements Engineering - for RR | This WBS element covers activities to define and document external interface requirements for the TM as part of an Integrated Task Team. Technical participation in the Interface Development Teams. Refer to TM Work Identification Matrix “Define External Interface Requirements” process. Deliverable: - TM External IRDs (Interface Requirement Documents)
5. SKA.TEL.MGR.SE.PDR.EIRD - Telescope Manager Define External Interface Requirements
| 5. SKA.TEL.MGR.SE.ARC - Telescope Manager Architectural Design |  | Precursor understanding and integration evaluation.
|  | 6.SKA.TEL.MGR.SE.ARC.PREC | This WBS element covers architectural design activities during stage 1 Concept Definition. A limited set of implementation options are defined, options traded off, and a small number of options are selected, that can be taken forward to preliminary design, based on cost, performance and risk. A first order design description is produced for selected options. Refer to processes “Architectural Design” in the TM work identification matrix. Deliverable: -First order TM Options Tradeoff Document
|  | 6. SKA.TEL.MGR.SE.ARC.CONCEPT - Telescope Manager Architectural Design - concept definition | This WBS element covers architectural design activities during stage 1 Preliminary Design. A single architecture is selected, based on performance, cost and risk. A full design description of the selected option is developed. The architecture of the selected option is evaluated. This TM Design Report will focus on the core TM requirements and may exclude or only lightly cover requirements that are only required at a later stage, like observation preparation and proposal management. Refer to processes “Architectural Design” in the TM work identification matrix. Deliverables: - TM Design Report, - TM Configuration Item List
|  | 6. SKA.TEL.MGR.SE.ARC.PDR - Telescope Manager Architectural Design - for PDR | This WBS element covers activities to participate in defining the implementation details of TM external interfaces as part of Integrated Task Teams for PDR. Deliverables: - TM External ICDs (Interface Control Documents)
| 5. SKA.TEL.MGR.SE.PDR.EICD - Telescope Manager Define External Interfaces |  | This WBS element covers activities to Conduct a hazard analysis to identify specific design features that are required to ensure safe operation for the PDR. Deliverables: - TM Hazard Analysis Report
| 5. SKA.TEL.MGR.SE.PDR.HAZ - Telescope Manager Hazard Analysis |  | Prepare the report for the PDR. NOTE: Since it is assumed that TM equipment will be installed in RFI shielded facility, this is not needed. Deliverables: - TM EMC/RFI Analysis Report
| 5. SKA.TEL.MGR.SE.PDR.EMC - Telescope Manager EMC/RFI Analysis |  | This WBS element covers activities to perform a Failure Modes, Effects and Criticality Analysis with impact on availability and fault reporting for the PDR. Deliverables: - TM FMECA Report
| 5. SKA.TEL.MGR.SE.PDR.FMECA - Telescope Manager FMECA |  | This WBS element covers activities to perform a Reliability Availability and Maintainability analysis to: - identify possible redundancy requirements and - verify the design against reliability, availability and maintainability requirements - allocate reliability budget to architectural elements of the item Deliverables: - TM RAM Report
| 5. SKA.TEL.MGR.SE.PDR.RAM - Telescope Manager RAM Analysis |  | This WBS element covers activities to produce the TM Development Plan for the PDR: 1) Define development/implementation strategy * software implementation procedures, * software reuse, * software deployment strategy, * fabrication processes, * obsolescence guidelines from SKA Office, * standardisation guidelines from SKA Office. * Identify constraints that the implementation strategy and technology impose on the design solution. 2) Define testing and integration strategy * Define an assembly sequence and strategy that minimises system integration time, costs and risks, but that permits verification against a sequence of progressively more complete item configurations.- Identify the constraints on the design arising from the integration strategy. * Define deployment/rollout strategy 3) Define transition strategy * Prepare a transition strategy, including installation and commissioning of the item iaw agreements. * Prepare the site of operation iaw applicable health and safety, security and environmental regulations. Deliverables: - Preliminary TM Development Plan
| 5. SKA.TEL.MGR.SE.PDR.DEVP - Telescope Manager Prepare Development Plan |  | This WBS element covers activities to plan verification for the TM (including prototypes) for the PDR: - Define a strategy for qualification of the TM, - Define a strategy for verifying the TM entities throughout the life cycle, - Define a verification plan based on TM requirements, - Identify potential constraints, imposed by verification enabling systems, on design decisions. Deliverables: - Preliminary Verification Plan - Qualification and Roll-out Plan
| 5. SKA.TEL.MGR.SE.PDR.VERP - Telescope Manager Plan Verification |  | This WBS element covers activities to prepare a support concept for the TM (including prototypes), addressing: - Support Personnel - Support Publications - Maintenance task analysis - Support Training - Supply Support - Packaging, Handling, Storage and Transportation - Support and Test Equipment - Support Facilities Deliverables: - Preliminary TM Support Concept (maintenance plan)
| 5. SKA.TEL.MGR.SE.PDR.MNTP - Telescope Manager Plan Maintenance |  | This WBS element covers activities to: - Define a configuration management strategy - Identify items that are subject to configuration control Deliverables: - TM Configuration Management Plan
| 5. SKA.TEL.MGR.SE.PDR.CMP - Telescope Manager Plan Configuration Control |  | This WBS element covers verification activities up to PDR to: - perform Requirements verification - perform Preliminary Design verification - perform Other Documents verification Deliverables: - TM Statement of Compliance (Compliance Matrix)
| 5. SKA.TEL.MGR.SE.PDR.VER - Telescope Manager Perform Verification |  | This WBS element covers architectural design activities during stage 2 for Critical Design Review. Revisit TM Design Report and expand for further requirements and more functionality (e.g. addition of observation preparation and proposal management). Deliverables: - Updated TM Design Report, - TM Internal Interface Requirement Documents, - TM Internal ICDs (Interface Control Documents), - UpdatedTM Configuration Item List
|  | 6. SKA.TEL.MGR.SE.ARC.CDR - Telescope Manager Architectural Design - for CDR | This WBS element covers Requirements Engineering activities to update the full set of requirements for CDR stage. Deliverable: - Updated TM Requirement Specification (Level 3)
|  | 6. SKA.TEL.MGR.SE.RR.CDR Telescope Manager Requirements Engineering - revisit for CDR | This WBS element covers activities to participate in updating the implementation details of TM external interfaces as part of Integrated Task Teams for CDR. Deliverables: - TM External ICDs (Interface Control Documents)
| 5. SKA.TEL.MGR.SE.CDR.EICD - Telescope Manager Update External Interfaces |  | This WBS element covers activities to define the implementation details of TM internal interfaces. Deliverables: - TM Internal ICDs (including interface drawings as appropriate)
| 5. SKA.TEL.MGR.SE.CDR.IICD - Telescope Manager Define Internal Interfaces |  | This WBS element covers activities to update the hazard analysis to identify specific design features that are required to ensure safe operation for the CDR. Deliverables: - Updated TM Hazard Analysis Report
| 5. SKA.TEL.MGR.SE.CDR.HAZ - Telescope Manager Updated Hazard Analysis |  | Update the report for the CDR. Deliverables: - Updated TM EMC/RFI Analysis Report
| 5. SKA.TEL.MGR.SE.CDR.EMC - Telescope Manager Updated EMC/RFI Analysis |  | This WBS element covers activities to update the Failure Modes, Effects and Criticality Analysis with impact on availability and fault reporting for the CDR. Deliverables: - Updated TM FMECA Report
| 5. SKA.TEL.MGR.SE.CDR.FMECA - Telescope Manager Updated FMECA |  | This WBS element covers activities to update the Reliability Availability and Maintainability analysis for CDR to: - identify possible redundancy requirements and - verify the design against reliability, availability and maintainability requirements - allocate reliability budget to architectural elements of the item Deliverables: - Update TM RAM Report
| 5. SKA.TEL.MGR.SE.CDR.RAM - Telescope Manager Updated RAM Analysis |  | This WBS element covers verification activities up to CDR to: - Conduct qualification and verification of CDR implementations/prototypes to demonstrate compliance to the specified design requirements - Analyse, record and report verification, discrepancy and corrective action information - Probably through iterative cycles Deliverables: - TM Qualification Test Procedure - TM Verification Report - Issue tracking system in place for non-conformities and possible remedies - Updates to prototypes
| 5. SKA.TEL.MGR.SE.CDR.VER - Telescope Manager Perform Verification |  | This WBS element covers activities to provide a full design description for CDR. Deliverables: - Updated TM Design Report, - TM Configuration Item List
| 5. SKA.TEL.MGR.SE.CDR.DD - Telescope Manager Design Description |  | Updates to the TM Development Plan for CDR with: - Complete implementation planning. - Complete integration planning. - Complete transition planning. - Complete operations planning. Deliverables: - Final TM Development Plan - Final Qualification and Roll-out Plan
| 5. SKA.TEL.MGR.SE.CDR.DEVP - Telescope Manager Development Plan |  | Final verification planning for CDR. Deliverables: - Final TM Verification Plan
| 5. SKA.TEL.MGR.SE.CDR.VERP - Telescope Manager Plan Verification |  | Updates to the TM Support Concept for CDR with: - Complete maintenance planning. Deliverables: - Final TM Support Concept
5. SKA.TEL.MGR.SE.CDR.MNTP - Telescope Manager Plan Maintenance
4. SKA.TEL.MGR.TELMGT telescope management
| 5.SKA.TEL.MGR.TELMGT.SE - TM Telescope Management Systems Engineering |  | Deliverables: - Telescope Management Requirements Specification, including use cases
|  | 6.SKA.TEL.MGR.TELMGT.SE.RE - TM Telescope Management Requirements Engineering | Deliverables: - Telescope Managent Design Report, including software architecture models
6.SKA.TEL.MGR.TELMGT.SE.ARC - TM Telescope Management Architectural Design
|  | 6.SKA.TEL.MGR.TELMGT.SE.IICD - TM Telescope Management Define Internal Interfaces | Deliverables: - Telescope Managent Design Report, including software models
6.SKA.TEL.MGR.TELMGT.SE.DD - TM Telescope Management Detailed Design
6.SKA.TEL.MGR.TELMGT.SE.VER - TM Telescope Management Verification
5 SKA.TEL.MGR.TELMGT.MON - Monitoring data acquisition and handling
5. SKA.TEL.MGR.TELMGT.CTRL – Control
5. SKA.TEL.MGR.TELMGT.DTM - Data Model support
5. SKA.TEL.MGR.TELMGT.UIS - Operator and Engineer interfaces
5. SKA.TEL.MGR.TELMGT.LMC - Local M&C Interface standardisation
5. SKA.TEL.MGR.TELMGT.OPDBS - Operations Support databases
5. SKA.TEL.MGR.TELMGT.OPSUPP - Operations Support
5. SKA.TEL.MGR.TELMGT.ARCH - Monitoring data archive
5. SKA.TEL.MGR.TELMGT.FAULT - Fault detection and management
5. SKA.TEL.MGR.TELMGT.SAFE - Safety and asset protection
5. SKA.TEL.MGR.TELMGT.SEC - Security
5. SKA.TEL.MGR.TELMGT.REL - Reliability, availability and integrity
5. SKA.TEL.MGR.TELMGT.ENGSIM - Engineering device simulators
5. SKA.TEL.MGR.TELMGT.PLAT - Platform Specification
4. SKA.TEL.MGR.OBSMGT telescope manager observation management
| 5.SKA.TEL.MGR.OBSMGT.SE - TM Observation Management Systems Engineering |  | Deliverables: Observation Management Requirements Specification, including software use cases
|  | 6.SKA.TEL.MGR.OBSMGT.SE.RE - TM Observation Management Requirements Engineering | Deliverables: Observation Management Design Report, including software architecture models
|  | 6.SKA.TEL.MGR.OBSMGT.SE.ARC - TM Observation Management Architectural Design | Deliverables: Observation Management Design Report, including software models
6.SKA.TEL.MGR.OBSMGT.SE.DD - TM Observation Management Detailed Design
|  | 6.SKA.TEL.MGR.OBSMGT.SE.VER - TM Observation Management Verification | This item would cover the definition of Proposal Submission for the telescope, but it seems that proposal submission and observation preparation are currently excluded from this element, until the ConOps group conclude on what is needed. Proposal handling also needs to be included when ConOps reports.
| 5. SKA.TEL.MGR.OBSMGT.PROPSUB - Proposal Submission |  | This item would cover the definition of Observation Preparation for the telescope, but it seems that proposal submission and observation preparation are currently excluded from this element, until the ConOps group conclude on what is needed.
| 5. SKA.TEL.MGR.OBSMGT.OBSPREP - Observation preparation |  | Responsibilities - Identify observations suitable for observing - Select observation to be observed - Despatch observation to execution - Track execution - Update status of observations and projects - Inform downstream (SDP archive?) of execution completion - Manage creation, use and destruction of sub-arrays. - Manage telescope/instrument resources Tasks: - Survey existing options (ALMA, JVLA,GMRT,ASKAP,MeerKat,LOFAR,...) - Define top level structure of a project - Use Cases and Detailed requirements - Design Stage 1 and Stage 2, including trade offs - Design Reports 1 and 2 - Reviews
| 5. SKA.TEL.MGR.OBSMGT.SCHED - Scheduling |  | Responsibilities: - Configure "instruments" for taking data (includes other components) - Tel Mgt M&C - CSP - SDP - ... Tasks - Identify interfaces requiring configuration - Define interface content - Identify candidate technologies - Trade off and decide on technology
| 5. SKA.TEL.MGR.OBSMGT.CFG - Instrument configuration |  | Responsibilities: - Manage the execution of a single observation execution - Ingest an observation description - Configure subsystems/components (cf. Instrument Configuration?) - Coordinate and sequence subsystems/components - Execute observation icw TELMGT.CTRL (boundary needs to be determined) - Collect &time stamp meta-data - Despatch meta-data to SDP/Archive - Manage CSP despatch of visibilities, time series, etc. to SDP/Archive Tasks: - Identify boundaries, esp. with TELMGT.CTRL - Survey existing options (ALMA, JVLA, GMRT, ASKAP, MeerKat...) - Define basic structure of an observation - Use Cases and requirements - Design 1 & 2 - Identify candidate technologies - Trade off and decide on technology
| 5. SKA.TEL.MGR.OBSMGT.EXEC - Observation execution |  | Responsibilities: - Store data items required by observation management - Allow effecient query and retrieval of items Tasks: - Identify data items - Design data models (overlap/interface with others) - Identify candidate technologies - Trade off and decide on technology
| 5. SKA.TEL.MGR.OBSMGT.ARCH - Observation management data archive |  | Responsibilities - Provide user interfaces to: - scheduling - observation execution - project and observation lifecycle management - overview of TELMGT.MON ? - ... Tasks - Identify user interfaces required - Detailed requirements - Design - Identify candidate technologies - Trade off and decide on technology
| 5. SKA.TEL.MGR.OBSMGT.UI - User interface |  | Responsibilities - Simulate an observation - Times, data rates, data volumes all to be captured. Tasks: - Detailed Requirements capture - Design
| 5. SKA.TEL.MGR.OBSMGT.SIM – Simulation (observation simulation) |  | Tasks: - Identify candidate technologies - Include Operating System, Hardware, estimated processing needs, Power requirements, cost - Trade off and decide on technology
| 5. SKA.TEL.MGR.OBSMGT.PLAT - Platform Specification |  | Refer to [3], Table 3 for definitions of Technology Readiness Levels (TRL).
4. SKA.TEL.MGR.PROT telescope manager prototypes |  |  | This WBS element covers activities necessary to design, procure, assemble and integrate TRL1 to TRL5 models required for TM Concept Exploration during Concept Definition. Typical examples are prototypes to evaluate database technologies, evaluate monitoring and control frameworks e.g. EPICS, etc.
| 5.SKA.TEL.MGR.PROT.CON - Concept/Technology Prototypes |  | This WBS element covers activities necessary to design, procure, assemble and integrate TRL4 models required for early integration of TM with other elements.
|  | 6.SKA.TEL.MGR.PROT.CON.DES - TM Design Concept Prototypes Design | Deliverables: - Software libraries used to demonstrate TM Element compliance Software: - Establish deployment environment for software. - Develop/adapt software and compile, inspect, deploy to target hardware and test to assure conformance to design criteria.
6.SKA.TEL.MGR.PROT.CON.IMP - TM Design Concept Prototypes Perform Implementation
6.SKA.TEL.MGR.PROT.CON.INT - TM Design Concept Prototypes Perform Integration
6.SKA.TEL.MGR.PROT.CON.VER - TM Design Concept Prototypes Perform Verification
5.SKA.TEL.MGR.PROT.INT - Integration Prototypes
|  | 6.SKA.TEL.MGR.PROT.INT.DES - TM Design Integration Prototypes Design | Deliverables: - Software libraries used to demonstrate TM Element compliance Software: - Establish deployment environment for software. - Develop/adapt software and compile, inspect, deploy to target hardware and test to assure conformance to design criteria.
6.SKA.TEL.MGR.PROT.INT.IMP - TM Design Integration Prototypes Perform Implementation
6.SKA.TEL.MGR.PROT.INT.INT - TM Design Integration Prototypes Perform Integration
6.SKA.TEL.MGR.PROT.INT.VER - TM Design Integration Prototypes Perform Verification
5.SKA.TEL.MGR.PROT.QR - Qualification Prototype
|  | 6.SKA.TEL.MGR.PROT.QR.DES - TM Qualification Prototype Design | Deliverables: - Software libraries used to demonstrate TM Element compliance Software: - Establish deployment environment for software. - Develop/adapt software and compile, inspect, deploy to target hardware and test to assure conformance to design criteria.
6.SKA.TEL.MGR.PROT.QR.IMP - TM Qualification Prototype Perform Implementation
6.SKA.TEL.MGR.PROT.QR.INT - TM Qualification Prototype Perform Integration
6.SKA.TEL.MGR.PROT.QR.VER - TM Qualification Prototype Perform Verification
6.SKA.TEL.MGR.PROT.QR.TRA - TM Qualification Prototype Perform Transition
6.SKA.TEL.MGR.PROT.QR.OPER - TM Qualification Prototype Operation
6.SKA.TEL.MGR.PROT.QR.DISP - TM Qualification Prototype Disposal
4. SKA.TEL.MGR.LMC telescope manager local monitoring and control
5.SKA.TEL.MGR.LMC.SE - TM Local Monitoring and Control Systems Engineering
6.SKA.TEL.MGR.LMC.SE.RE - TM Local Monitoring and Control Requirements Engineering
|  | 6.SKA.TEL.MGR.OBSMGT.SE.IICD - TM Observation Management Define Internal Interfaces | Deliverables: - Local Monitoring and Control Design Report, including software models
6.SKA.TEL.MGR.LMC.SE.ARC - TM Local Monitoring and Control Architectural Design
6.SKA.TEL.MGR.LMC.SE.IICD - TM Local Monitoring and Control Define Internal Interfaces
|  | 6.SKA.TEL.MGR.LMC.SE.IMP - TM Local Monitoring and Control Detailed Design | Deliverables: - Local Monitoring and Control Design Report, including software models
|  | 6.SKA.TEL.MGR.LMC.SE.VER - TM Local Monitoring and Control Verification | Deliverables: - Local Monitoring and Control Design Report, including software models
6.SKA.TEL.MGR.LMC.SE.DD - TM Local Monitoring and Control Detailed Design
5.SKA.TEL.MGR.LMC.MON - TM Monitoring and Control: Monitor
5.SKA.TEL.MGR.LMC.CON - TM Monitoring and Control: Control
5.SKA.TEL.MGR.LMC.DIAG - TM Monitoring and Control: Diagnostics
| 5.SKA.TEL.MGR.LMC.PLAT - Platform Specification |  | [From [1] “Local infrastructure includes all necessary equipment and installations required by the telescope manager to operate (e.g. cable ducts, internal networks etc). MGR local infrastructure does not include the provision of buildings and air-conditioning units. Local infrastructure includes all safety systems necessary to assure the safety of the personnel and hardware involved throughout the lifetime and all operational scenarios.”]
4. SKA.TEL.MGR.LINFRA telescope manager local infrastructure |  |  | Deliverables: - Local Infrastructure Requirements Specification
5.SKA.TEL.MGR.LINFRA.SE - TM Local Infrastructure Systems Engineering
6.SKA.TEL.MGR.LINFRA.SE.RE - TM Local Infrastructure Requirements Engineering
6.SKA.TEL.MGR.LINFRA.SE.VER - TM Local Infrastructure Verification
6.SKA.TEL.MGR.LINFRA.SE.ARC - TM Local Infrastructure Architectural Design
|  | 6.SKA.TEL.MGR.LINFRA.SE.IICD - TM Local Infrastructure Define Internal Interfaces | Equipment racks, etc. that house TM equipment.
| 5.SKA.TEL.MGR.LINFRA.HSG - TM Local Infrastructure Hardware Housings |  | Distribution of Cooling within the TM.
| 5.SKA.TEL.MGR.LINFRA.CLG - TM Local Infrastructure Cooling |  | Distribution of electrical power within TM.
| 5.SKA.TEL.MGR.LINFRA.PWR - TM Local Infrastructure Power |  | Distribution of signals within TM.
| 5.SKA.TEL.MGR.LINFRA.SIG - TM Local Infrastructure Signal Distribution |  | Distribution of timing signals within TM.
| 5.SKA.TEL.MGR.LINFRA.TIM - TM Local Infrastructure Timing |  | Safety systems required to assure the safety of personnel and hardware throughout the TM life cycles.
5.SKA.TEL.MGR.LINFRA.TIM - TM Local Infrastructure Safety